# Testing Methodology Overview for Implementation Roadmap

## Definition

Testing covers all activities during the implementation process which prove that system settings are correct. It includes test planning, conducting tests, and test documentation.

The main areas, which are relevant for testing, are:

- configuration of business processes

- development (conversions, interfaces, reports, etc.)

- system management (technical tests, performance tests)

Purpose

The purpose of the testing is to ensure your business processes run smoothly in the system according to the defined business requirements.

Subject Area Overview Table

| Phase | Work package or Activity group | Activities (Tasks) | Tools or Key Accelerators | Roles | Deliverables |
| --- | --- | --- | --- | --- | --- |
| 1 | Define Implementation Procedures | Define Testing Strategies | Testing Strategy White Paper | Project Manager, Business Process Team Lead, Technical Team Lead | Testing strategy paper |
| 3 | Baseline Scope Testing | Define Baseline Test Cases | BPP with test condition, Case Procedure, Test Scenario Template | Application Consultant, Business Process Owner | Baseline test case |
| 3 |  | Create Test Plan for Baseline | BPML Baseline Scope Worksheet | Application Consultant, Business Process Owner, Business Process Team Lead | Baseline test plan |
| 3 |  | Test Baseline | BPML Baseline Scope Worksheet | Business Process Owner | Validated Baseline |
| 3 | Final Scope Testing | Define Final Scope Test Cases | BPP with test condition, Case Procedure, Test Scenario Template | Application Consultant, Business Process Owner | Final Scope test cases |
| 3 |  | Create Test Plan for Final Scope | BPML Cycle 1-n Scope Worksheet | Application Consultant, Business Process Owner, Business Process Team Lead | Final Scope test plan |
| 3 |  | Test Final Scope | BPML Cycle 1-n Scope Worksheet | Business Process Owner | Validated Final Scope |
| 3 | Development Testing | Test Conversion Programs, Interface Programs, Enhancement Programs, Reports, Forms | Test section of Functional Specification, Development List | Technical Consultant, Business Process Owner | Validated programs and forms |
| 3 | Final Integration Test | Prepare Integration Test including define test scope, define test cases and test plan | Test Scenario Template, BPML Integration Test worksheets, Testing Strategy White Paper | Business Process Owner, Business Process Team Lead, Test Team Lead, Test Team Member | Final Integration test cases and test plan |
| 3 |  | Conduct and approve Integration Test | BPML Integration Test worksheets | Business Process Owner, Test Team Member | Validated system, that covers business processes requirements |
| 3 | System Testing | Develop system test plans for technical and performance tests | Checklists, Stress/Volume test sample plan, Stress Testing Strategy | Technical Consultant, Technical Team Lead, System Administrator, Business Process Team Lead | System test plans |
| 4 | System Testing | Conduct system tests |  | Technical Consultant; Business Process Owner, System Administrator | Tested and confirmed system |

Define Testing Strategies

### Definition

The testing strategy defines the requirements and goals of the R/3 configuration, determines the tools and methods used to check that the system responds correctly, determines how and when the test will be performed and recommends how the approval process should occur.

### Purpose

The purpose of this task is to create a document, which guides the project team through the implementation, and ensures that planning and conducting testing activities in the various phases and work packages is properly done.

### How to

The project manager or test team leader, if already in place, creates the document using the Testing Strategy White Paper as a guideline or example.

## Baseline Scope Testing

Definition

Baseline Scope testing includes

- testing of transactions and functions (unit testing)

- testing of business processes and scenarios (scenario testing).

With Baseline Scope testing you ensure that Baseline configuration is valid, and supports the business processes defined in the Blueprint.

### Purpose

The purpose of Baseline Scope testing activities is to plan and conduct testing to validate the Baseline configuration.

### How to

Baseline Scope testing is done in three steps:

- Define Baseline test cases:

- Process owners together with application consultants determine test cases, which reflect Baseline business processes.

- For simple transactions testing (unit testing) can be done straightforward during configuration and the results can be recorded in the corresponding BPML worksheet.

- Some transactions are very complex involving multiple screens, functions and variations to run. Those transactions (i.e. Sales order) can be documented and tested with a BPP, maintaining the test section with test conditions and variations of the standard transaction, or with Case Procedures, maintaining the test section.

- To document process flows (scenario testing) it is recommended using the Test Scenario template entering every single step (transaction) with input and output data.

- Create Baseline test plan:

- To organize and follow up the unit and scenario testing during Baseline the BPML Baseline worksheet can be used. Enter additional lines for each process or scenario variation, which has to be tested.

- Assign timeframes and resources for testing.

- Test Baseline:

- Use the Baseline test plan and the test cases to test Baseline configuration.

- Update the Baseline worksheet with status and completion date information.

## Final Scope Testing

### Definition

Final Scope testing includes

- testing of transactions and functions (unit testing)

- testing of business processes and scenarios (scenario testing).

Final Scope testing is done during the several cycles of Final Scope Configuration, and at the end of each cycle. With Final Scope testing you ensure that Final configuration is valid, and supports the business processes defined in the Blueprint.

### Purpose

The purpose of Final Scope testing activities is to plan and conduct testing to validate the Final Scope configuration.

### How to

Final Scope testing is done in three steps:

- Define Final Scope test cases:

- Process owners together with application consultants determine test cases, which reflect Final Scope business processes.

- Simple transactions can be tested straightforward during configuration and the results can be recorded in the corresponding BPML Cycle Scope worksheet.

- Complex transactions can be documented and tested with a BPP, maintaining the test section with test conditions and variations of the standard transaction, or with Case Procedures, maintaining the test section.

- To document process flows the Test Scenario template can be used entering every single step (transaction) with input and output data.

- Create Final Scope test plans:

- To organize and follow up testing during Final Scope configuration the BPML Cycle 1-n Scope worksheets can be used. Enter additional lines for each process or scenario variation, which has to be tested.

- Assign timeframes and resources for testing.

- Test Final Scope:

- Use the Final Scope test plan (cycle plans) and the test cases to test Final configuration.

Update the Cycle 1-n Scope worksheets with status and completion date information.

## Development Testing

### Definition

Unit testing of customer-specific development.

- Conversions

- Interfaces – Third-party

- Interfaces – Legacy

- Interfaces – Online (EDI, ALE, Internet)

- Enhancements (User-exits and other code enhancements)

- Reports

- SAPScript forms

Testing of development is done in the realization phase during the development of conversions, interfaces, enhancements, reports, and forms to ensure that the programs work properly according to the requirements defined in the functional specification, and in the corresponding business process documentation.

After development unit testing is completed all customer-specific programs and forms have to be included in the Final Integration Test.

### Purpose

The purpose of development testing activities is to plan testing, create test data, and conduct testing.

### How to

To define test requirements, test data and test results during the unit test, use the test section of the Functional Specification document. For integration test each development has to be included in a special test scenario to ensure that the whole business flow works (see Final Integration Test).

To organize the testing of all developments use the Development Master List and update responsibilities and dates for testing. Create links to all corresponding documents (Functional Specification, Test Scenario).

Development should not only be tested by the developer but also by the process owner  to make sure that the test results (output data) are correct, and reflect the business processes defined in the Blueprint.

## Final Integration Test

### Definition

Final integration testing is accomplished through the execution of predefined business flows, or scenarios, that emulate how the system will run your business. These business flows, using migrated data from the pre-existing systems, will be performed in a multifaceted computing environment comprised of R/3, third-party software, system interfaces and various hardware and software components. It is this environment that builds the necessary level of confidence that the solution is complete and will perform in your business.

Final Integration testing focuses on cross-functional integration points, as well as end-to-end business processes. A well defined Final Integration test plan starts with the testing of the cross-functional integration points (touch points) and ends with the end-to-end testing of critical business processes identified within the Business Blueprint.

### Purpose

The purpose of the Final Integration Test is to plan and execute the final integration test. This is important for the functional verification of your production system. It should be a simulation of live operations.

### How to

Final Integration testing is recommended to be done in two iterations. The first iteration (Integration Test 1) concentrates on testing all important business processes inside the R/3 system, starting with touch point scenarios and ending with end-to-end-scenarios.

If customer specific development like user-exits and transactions is already finalized and unit tested, it should be included in the first iteration. Authorizations and user roles should be also tested in the Integration Test 1.

Integration Test 2, as a second iteration, focuses on the most important cross-enterprise scenarios with touch points to external components, including testing of conversions, interfaces, reports, forms (SAPScript), EDI, ALE, and the necessary authorizations.

Final integration tests need to be an evolutionary process that is driven from your previous testing efforts. The test cases and scenarios that were used for Baseline and Final Configuration need to be reviewed and enhanced for the integrated test. These selected cases can be combined to represent a business process flow such as a revenue cycle or a material acquisition cycle. Problems encountered during these efforts also need to be tested under an integrated environment. Final Integration test cannot be viewed as an independent, but as a capstone effort that brings together and builds upon all previous testing efforts.

Refer to the Testing Strategy White Paper to get more information how to set up Final Integration Test.

## System Testing

### Definition

System testing consists of technical tests and performance related tests. The technical tests aim to validate that the technical components of the production environment are working properly. These tests include validating the system administration procedures, failure recovery, and disaster recovery. The performance related tests include volume and stress testing of business transactions and business transaction input / output using printer and fax devices.

### Purpose

The purpose of the system testing activities is to create test plans for technical and performance testing (Phase 3), and to conduct these tests (Phase 4 to prepare the production environment).

### How to

There is no special tool provided by ASAP to organize technical testing. The system administrator and/or the project manager can use the project plan to plan the several types of system test.

In the Roadmap there are some checklists and sample plans which provide additional information on how to test.

Performance related testing (stress and volume test) should be planned and conducted from the technical team together with the application teams to ensure that the important business processes are covered.