## Rollout Methodology Overview for Global Roadmap

### Definition

The Rollout Subject Area pertains to planning and staging done in the Global project in preparation for the Rollout projects that are to follow. Tasks in this subject area occur before the Rollout project has officially started, but assumes that some preliminary personnel have been identified.

### Purpose

In a global project during Global Business Blueprint, the initial preparation begins for the Rollout project, which has not yet actually started, and therefore has no official budget or staff. It is at this point that the rollout planning criteria, preliminary schedule and modeling concerns begin to be addressed.

The global blueprinting process and template development must also proceed by including appropriate local input during the global project. Just how much local input is appropriate is determined during the Customer Solution Strategy (CSS), and may include few or many sites. In the later case in particular, the roll of Global Rollout Manager is created to keep focus. The Global Rollout Manager, together with the appropriate local representatives on the global team, handles communications with local sites during the global program.

Other tasks related to the Rollout Subject Area concern supporting the Rollout project itself once it has been officially started, and handling upgrades to the Template as input is returned from the Rollout project.

#### Rollout Overview Table

| Phase | Work Package or Activity Group | Activities | Tools or Key Accelerators | Roles | Deliverables | (optional) System/ Environment |
| --- | --- | --- | --- | --- | --- | --- |
| 2 |  | Phase 2: Global Business Blueprint |  |  |  |  |
|  | 2.2 | Early Rollout Preparation | Global Rollout Plan for R/3 Systems | Program/project manager Global Support Manager Global Rollout Manager | Preliminary Rollout Plan Preliminary Resource Plan Preliminary Budget Plan |  |
|  | 2.6 | Global Business Process Definition | High level enterprise scope as defined during the Customer Solution Strategy Global Solution Package - BOM Global Solution Package Index | Program/project manager Global Support Manager Global Rollout Manager | Approach to defining global and local processes Key Internationalization issues |  |
|  | 2.7 | Develop Global Environment | Preliminary architecture results from CSS including: Anticipated links between SAP and non-SAP systems. Future Application Architecture Interface Techniques & Characteristics | Program/project manager Global Rollout Manager Technical Consultant | Revised architecture scope including: Issues brought forward by local considerations not previously included |  |
| 3 |  | Phase 3: Global Realization |  |  |  |  |
|  | 3.13 | Rollout Preparation | Tested Template | Program/project manager Global Support Manager Global Rollout Manager | The outcome of this activity is a packaged solution ready for delivery to local sites to be used for local projects |  |
|  | 3.14 | Execute Rollout | Final Rollout Plan for designated sites Completed Workshop Content Completed Template | Global Rollout Manager Rollout Project Manager Consultants and Facilitators | workshops to provide local rollout project teams with a workshop covering information about the program as well as information to kickoff local implementation projects |  |
| 4 |  | Phase 4: Global Maintenance and Support |  |  |  |  |
|  | 4.2 | Rollout Support |  | Global Rollout Manager Rollout Project Manager Consultants and Facilitators | The CCC is set up and provides support to the local implementation teams. |  |
|  | 4.3 | Upgrade Template Version | Initial solution package of the current version of global template has been packaged already Local rollout project is ongoing or local site is already operational | Global Rollout Manager Rollout Project Manager Consultants and Facilitators | Solution alternatives are evaluated and related costs, resources etc. estimated Decision about solution approach (which alternative, when, by whom) Decision about solution rollout approach (in which sequence, by whom) |  |